## Detailed Workplan
Detailed Work Plan Template
Initiative Name and Description | HHS Porter Process Simulation - Student Project
Version: | 1
Legend
| Status |  |  | Type
| On-Track |  |  | HHS
| Complete |  |  | Capstone
Pending
Late
TBD
Milestone | Num. | Description | Directly Responsible Person(s) | Dependecy | Projectetd Start Date | Projected End Date | Duration (Days) | Status | Comments
Winter Break
Design Documentation Revision 0 | 1 | Revision 0 of the design documentation to be completed by students for the course | Students | NA | 2014-01-06 | 2014-01-14 | 8
Software Development | 2 | Receive sample data from HHS | HHS | NA | 2014-01-06 | 2014-01-13 | 7 |  | we need the sample data sometime during this period week
Software Development | 3 | Develop proof on concept version based on current requirements, and sample data | Students | 2 | 2014-01-06 | 2014-01-24 | 18
Software Development | 4 | Deliver first demo to HHS representatives | Students/HHS | 3 | 2014-01-27 | 2014-01-31 | 4 |  | set up a meeting sometime between these dates
Revision 0 Demonstration | 5 | Students deliver a demonstration for the course | Students | 1 | 2014-01-14 | 2014-02-07 | 24
Software Development | 6 | Receive feedback from HHS | HHS | 4 | 2014-01-31 | 2014-02-07 | 7 |  | receive feedback sometime during this period
Software Development | 7 | Meet withh HHS representatives to discuss feedback and additional requirements, if any | Students/HHS | 6,5 | 2014-02-08 | 2014-02-14 | 6 |  | set up a meeting sometime during this period
Software Development | 8 | Develop final version of the product | Students | 7 | 2014-02-15 | 2014-03-24 | 37
Revision 0 User Manual | 9 | Students create the first version of the user manual for the course | Students | 5 | 2014-02-07 | 2014-02-18 | 11
Test Report Revision 0 | 10 | Student deliver a first version of the test results for the software for the course | Students | 9 | 2014-02-18 | 2014-03-04 | 14
Software Development | 11 | Deliver second demo of the product to HHS staff | Students | 8 | 2014-03-17 | 2014-03-21 | 4 |  | set up a meeting during this time period
Software Development | 12 | Receive final feedback from HHS | HHS | 11 | 2014-03-17 | 2014-03-24 | 7 |  | feedback required
Software Development | 13 | If possible, apply minor changes according to feedback | Students | 12 | 2014-03-17 | 2014-03-24 | 7
Software Documentation | 14 | Develop software design documentation + user manual | Students/ICT/QS | 7 | 2014-01-06 | 2014-03-24 | 77
Software Testing | 15 | Lead usability tests with users of the product | Students/HHS | 12 | 2014-03-24 | 2014-03-28 | 4 |  | complete within this period
Software Testing | 16 | Perform scenario/stress tests on final product | Students | 12 | 2014-03-24 | 2014-03-28 | 4 |  | complete within this period
Revision 1 Final Demonstration | 17 | Capstone Milestone | Students | 10 | 2014-03-04 | 2014-03-30 | 26
Revision 1 Final Documentation | 18 | Capstone Milestone | Students | 10 | 2014-03-04 | 2014-03-30 | 26
Final Delivery | 19 | Provide final project report + design documentation + user manual + Final Demonstration | Students | 13,14,15,16 | 2014-04-14 | 2014-04-18 | 4
Final Delivery | 20 | Install final version of software on department computers | Students | 14,15 | 2014-04-14 | 2014-04-18 | 4